## Sheet1
User Acceptance Testing Checklist
Done? | Outcome | Tasks
Preparing the App for UAT
Double-check email "to" fields and external workflow groups.
Set up dashboards.
Prepare the access link (from your project teams).
Prepare for UAT kick-off meeting
Identify who the testers will be. This will be a diverse, small group of end-users.
Send a calendar invite to all testers.
Add the feedback log to a collaborative space with a share link.
Prepare the slides for UAT kick-off.
Double-check the browsers that end-users will be using. Google Chrome is recommended.
Kick-off UAT testing
Set up accounts for testers required to log in with the correct permission level.
Add users to the project team and workflow groups.
Send an email to summarise the meeting with the slides attached.
Deployment Checklist
Done? | Key Outcome | Tasks
Prepare for deployment
If the author and the person responsible for maintaining the solution is different, prepare a handover
Update email "to" fields and workflow groups to the actual users
Embed the link into the relevant place - central hub, website etc.
Set up accounts for end-users
Add all necessary end-users to the project team
Update workflow group members
Post deployment maintenance
Provide a support model for end-users needing help. Contact Checkbox for a solution template to collect feedback.
For complex solutions, document complex logic (e.g. how the MERGEs and FILTERs function)
Identify the processes and people involved for publishing new versions